## Migration checklist
Data center migration checklist
The seven phases of a data center migration. Fill in Status, Owner, Due date, and Notes.
Phase | Check | Done when | Status | Owner | Due date | Notes
1. Scope | Workloads to move, retain, and retire listed | Signed-off inventory
1. Scope | RPO, RTO, cutover window, and budget set | Written targets per application tier
2. Discovery | Inventory of servers, storage, and network paths complete | Inventory matches monitoring data
2. Discovery | Dependency mapping done per application | Machine groups defined for each wave
2. Discovery | Unsupported configurations flagged (SCSI bus sharing, physical-mode RDM) | Exceptions list with an owner per item
3. Strategy | Rehost, replatform, retire, or retain assigned per workload | Every workload has a strategy
4. Target | Network, firewall rules, and IP plan ready | Connectivity test between sites passed
4. Target | Compute, storage, identity, and security policies in place | Capacity covers peak load plus replication
4. Target | Source workloads backed up, restore tested | Restore test log
5. Replicate and test | Replication agents or appliances deployed | Every source machine visible in the migration tool
5. Replicate and test | Initial replication finished | All machines show a synced state
5. Replicate and test | Test migration run per application group | Test report with issues closed
6. Cutover | Maintenance window approved, users informed | Schedule and rollback criteria documented
6. Cutover | Final replica taken | Source shut down cleanly
6. Cutover | Workloads started at the target, acceptance testing done | Sign-off from application owners
6. Cutover | Client and DNS switch completed | Users reach the new site
7. Validate and exit | Performance compared with baselines, resources resized | Baseline report
7. Validate and exit | Monitoring, backup, and DR running at the new site | Alerts and jobs active
7. Validate and exit | Source kept read-only for the agreed rollback window | Rollback window end date recorded
7. Validate and exit | Lease, colocation, support, circuit, and license contracts closed | Termination confirmations on file
7. Validate and exit | Drives wiped or destroyed, asset records archived | Sanitization certificates
Progress
Checks total | 21
Marked Done | 0
Complete | 0%
Legend: yellow cells with blue text are yours to fill in. Status is a dropdown list.